# Risk Register: Teradata to GCP Migration (Telecom - Dallas, TX)

Estimated budget: $3.5M. Status: Planning phase. Use this register for workshop discussion and refinement.

| Risk Description | Probability | Impact | Mitigation | Owner | Status | Response Plan |
| --- | --- | --- | --- | --- | --- | --- |
| Incomplete inventory of Teradata assets due to limited legacy documentation | High | High | Perform targeted discovery with DBAs; allocate SMEs for undocumented areas; use automated schema scanners | Data Engineering Lead | Open | Immediate discovery sprint; escalate missing docs to Sponsor; schedule extended profiling window |
| Data loss during bulk migration or ETL translation | Medium | High | Implement checksum/hash reconciliation, row-count validation, and staged parallel runs; backup snapshots of source | Migration Lead | Open | Halt migration on discrepancies; restore from backups; run incremental re-sync |
| SQL dialect and stored procedure incompatibilities (Teradata->BigQuery) | High | High | Inventory stored procs/macros; use automated conversion tools and SME review; build a conversion validation framework | Data Platform Architect | Open | Prioritise business-critical queries for manual conversion; allocate spike tasks for complex macros |
| Performance regressions post-migration impacting SLAs | High | High | Establish performance baselines; run benchmarking; design slot reservations and BI Engine; query tuning cadence | Performance Engineer | Open | Rollback to Teradata for critical workloads; increase BigQuery resources temporarily; create optimization tickets |
| Regulatory non-compliance (SOX/HIPAA/CPNI handling) | Medium | High | Engage Compliance early; document controls; enforce masking and access controls; audit logging via Cloud Logging | Compliance Lead | Open | Pause deployments for non-compliant domains; remediate controls and re-audit |
| CPNI exposure due to incomplete masking or misconfigured views | Medium | High | GCP compliance team to implement masking for CPNI; review views and RBAC; test with privileged access workflows | Security Lead | Open | Revoke problematic views; reimplement masking; notify affected stakeholders |
| Vendor SLA gaps for migration tooling or managed services | Medium | Medium | Document required SLAs; maintain contingency vendors; negotiate interim terms; include penalties | Procurement Lead | Open | Escalate to Vendor Management; open change order or procure alternatives |
| Third-party BI tool compatibility and re-pointing risks | Medium | Medium | Early testing with Tableau/Looker/Power BI; create connector templates; vendor engagement for drivers | Integration Lead | Open | Maintain dual connections during parallel run; provide fallback reports |
| Insufficient SME availability (20% allocated to opex) | High | Medium | Resource levelling; hire/contract temporary specialists; protect key SME time in schedule | Resource Manager | Open | Reprioritise waves; request budget for contractors; escalate staffing to Sponsor |
| Fixed timeline pressure causing rushed validation | High | High | Build formal quality gates; reserve buffer time in waves; obtain executive buy-in for scope-based trade-offs | Project Manager | Open | Defer non-critical waves; request timeline extension or reduce scope |
| Data quality issues discovered late during UAT | Medium | High | Early profiling and data quality rules; create data repair playbooks; involve business SMEs | Data Governance Lead | Open | Implement corrective ETL rules; quarantine affected datasets; schedule remediation sprints |
| Security misconfigurations in GCP IAM or VPC exposing data | Medium | High | Use least privilege, org policy constraints, VPC Service Controls, and periodic security reviews; automated scanning | Cloud Security Lead | Open | Revoke offending permissions; apply emergency org policies; conduct forensics |
| Cost overruns due to unexpected BigQuery or Storage usage | Medium | Medium | Set budget alerts, cost governance, use reservations, and run cost modelling; enforce dataset lifecycle policies | Finance Lead | Open | Throttle heavy queries; enable cost controls; request contingency budget |
| Incomplete auditability or logging for regulatory evidence | Low | High | Design logging requirements early; enable Cloud Logging and export logs to immutable storage; validate retention policies | Compliance Lead | Open | Enable missing logging, rebuild audit trails where possible, notify auditors |
| Parallel run complexity causing data divergence between Teradata and BigQuery | Medium | Medium | Define clear dual-write or reconciliation strategy; frequent sync checkpoints; automated diff reports | Migration Lead | Open | Freeze cutover until divergence resolved; fallback to latest consistent snapshot |
| Decommissioning errors causing accidental loss of production Teradata data | Low | High | Controlled decommission runbook, approvals, and hold periods; preserve backups and retention snapshots | Operations Lead | Open | Immediately restore from snapshot; delay decommission until validation complete |
| Legal or contract constraints with Teradata licensing during migration | Low | Medium | Review contracts early with Legal; plan license transition; budget for buyouts if required | Legal/Procurement | Open | Negotiate transitional license terms; allocate legal support |
| Integration breaks for upstream systems still pointing to Teradata | Medium | Medium | Inventory consumers; communicate cutover schedule; provide APIs/replication where needed | Integration Lead | Open | Repoint affected systems; maintain hybrid access during transition |
| Resistance to change and lack of business adoption post-migration | Medium | Medium | Change management plan, training, and stakeholder engagement; early demos and pilot wins | Change Lead | Open | Run targeted training; collect feedback; provide business escalation routes |
| Backup/restore and DR strategy not validated in cloud | Low | High | Implement and test DR runbooks; RTO/RPO validation; regional replication if required | DR/Operations Lead | Open | Trigger DR drills; failover to standby; remediate gaps |
| Dependency on single vendor/tool for SQL conversion creating lock-in risk | Medium | Medium | Evaluate multiple tools; keep conversion artifacts portable; include source control for conversion scripts | Tooling Lead | Open | Switch to fallback tooling; roll back to manual conversion for critical items |